## 2legit2Quit_sprint1
Sprint 1
meeting # | Date | Time | Absent | Agenda | Report | Conclusion
Meeting 1 | 2024-07-02 | From 6:00PM to 7:00PM (1 hours) | Houssam Ait Idir 40155665 | we need to edit the Readme and include everyone Background -we need to divide the teams -we need to come up with the User Stories -we need to derive tasks from those User Stories -we created the Meeting Minutes Spread Sheet -we will creat the Member Contribution for each memeber -we need to plan for next sprint | -We edited the ReadMe file, -Created the Wiki page containing the Meeting Minutes. -We Divided the tasks, -created a excel sheet for the meeting minutes and user stories -We made sure that Houssam had a review of what we did in this meeting since he is not present to keep him updated and involved in this project. | -Tasks for sprint 1 were successfully accomplished. -Progress includes editing the ReadMe, team formation, user story initiation and documentation setup. -Houssam was kept informed despite of absence, ensuring project involvement. -Ready to procceed with planning for the next sprint.

## 2legit2Quit_sprint2
Sprint 1
meeting # | Date | Time | Attendes | Agenda | Report | Conclusion
Meeting 1 | 29/2/2024 | From 7:00PM to 8:00PM (1 hours) | Adib akkari Valentin Gornostaev | Created a catalogue to see the car database , added admin access, created basic html and css to show the catalogue | Adib reviewed the code and tested it throughly, decided whats next to work on, merged the branch with the main one and created a new branch to add more features, | Valentin did an excenllent job at creating the catalogue.
Meeting 2 | 2024-05-03 | 9:00 PM to 10:00 PM | Adib akkari , Valentin Gornostaev, Steven Gourgy, Houssam Ait Idir | Needs to make a second meeting to work on the integration of frontend and backend | the front end team and the backend team needs to merge their work and configure the frameworks | Steven did an excelent job at making the front end
Meeting 3 | 2024-07-03 | 8:00 PM till 9:00 PM | Adib akkari, Steven gourgy, valenti Gornostaev | The issue is solved and we will continue working | the backend needed to communicate with the front end | Steven solved the issue so we could continue the work
Meeting 4 | 2024-11-03 | 5:00 PM to 6:00 Pm | All team | we need to fix some issues with Admin screen | Adib going to work on CRUD operations for Products | Need more work before the deadline
Meeting 5 | 2024-11-03 | 11PM to 12 PM | Adib , Steven , Valentin | nothing Sprint 2 done | Reviewed the sprint 2 and submitted the Video for gradding | The team did a good job