## Sprint 1
Sprint 1
Member | Date | What did he/she do? | Time spent
Adib akkari | 2/2/2024 | created the github repositry and added everyone | 5 minutes
Houssem | 2/2/2024 | created a discord server and invited all memebers | 5 minutes
Everyone | 7/2/2024 | Came with the 6 User Stories during first meeting | 5 minutes
Everyone | 7/2/2024 | Dived the US into Tasks and added other attributes | 15 minutes
Adib and Steven | 9/2/2024 | Added the US and Tasks into issues in Discord | 30 minutes
Valentine | 9/2/2024 | Made and finalized the project approach and technology document | 30 minutes
Buhinka | 9/2/2024 | Created the spreadSheet for the team Contribution | 15 minutes
Houssem and adib | 9/2/2024 | Planned for next week Wiki | 15 minutes

## Sprint2
Sprint 1
Member | Date | What did he/she do? | Time spent
Valentin | 26/2/2024 | created a prototype of how to make the backend | 2 hours
Steven | 26/2/2024 | started the front end and backend and made a simple catalogue | 5 hours
Adib | 6/3/2024 | adding, editing, deleting Cars, register User | 3 hours
Steven | 8/3/2024 | Added redux for store | 2 hours
Valentin | 11/3/2024 | Added reservasion functionalitites | 6 hours
Houssam | 8/3/2024 | Front End User authentication (log in, log out, register) | 4 hours
Adib | 8/3/2024 | Backend User atuhentication (log in, log out, register) | 3 hours
Adib | 9/3/2024 | added Unit tests for Backend | 2 hours
Steven | 11/3/2024 | fixed issues within Houssam code | 2 hours
Bhumika | 10/3/2024 | Admin screen, listing existing users, managing users, deleting users | 5 hours
Adib | 11/03/2024 | Adding product list, edit, read, create, update products | 2 hours
Steven | 11/03/2024 | Fixed issues with CRUD operations on users | 2 hours
Valentin and steven | 11/03/2024 | Fixed issues with CRUD operations on products | 2 hours
Valentin | 11/03/2024 | Added CRUD operations on Reservations | 3 hours
Adib | 11/03/2024 | fixing merge issues | 1 hour
Steven and valentin | 11/03/2024 | filmed the video | 30 minutes